ASMF/DMF Working Group

Work Plan

Updated: 8 October , 2014 (draft)

Part I - Short Term Goals:

| Project # | Detailed Deliverable | Activity | Tasks | Milestone | Required completion Date | Lead person |
| --- | --- | --- | --- | --- | --- | --- |
| Deliverable - Establishment of the Working Group (WG) |
| 1 | Acceptance of working group mandate document. | Drafting and agreement of an ASMF/DMF WG Mandate document | Drafting of ASMF/DMF WG Mandate document. | - | Completed | Co-Chair (TGA) |
|  |  |  | Endorsement by ASMF/DMF WG members | - | Completed |  |
|  |  |  | Finalisation of ASMF/DMF WG Mandate document | Mandate accepted with revision to PMDA reference, to be confirmed Tuesday | Completed |  |
|  |  |  | Presentation and endorsement of the ASMF/DMF WG Mandate document to the IGDRP Steering Committee | Uploading of a finalised ASMF/DMF WG Mandate document to the Share Point site (SP) | Completed |  |
| 2 | Acceptance of ASMF/DMF working group members list | Drafting, circulation, and finalisation of ASMF/DMF WG membership list | Circulation of ASMF/DMF WG membership list (and contact information) for comments | - | Completed | Co-Chair (TGA) |
|  |  |  | Finalisation of ASMF/DMF WG membership list | Uploading of a finalised ASMF/DMF Working Group Membership list to the SP site. | Completed |  |
| Deliverable – WG Survey |
| 3 | Survey of ASMF/DMF requirements and systems among IGDRP members | Circulation of a single survey covering information required from all deliverables | Circulation of draft Gap Analysis Survey |  | Completed | PMDA |
|  |  |  | Receipt of comments on draft Gap Analysis Survey |  | Completed |  |
|  |  |  | Circulation of finalised Gap Analysis Survey |  | Completed |  |
|  |  |  | Collation of comments for a summary document outlining Gap Analysis Survey | Circulation of a summary document outlining Gap Analysis Survey | Completed |  |
|  |  |  | Discussion on results of Gap Analysis Survey | Presentation a summary document outlining Gap Analysis Survey. | Completed |  |
|  |  | Collation and presentation of results | Final draft of Gap Analysis Survey presented for comment | Presentation of final draft of the Gap Analysis Survey to ASMF/DMF WG and Steering committee | 4 November 2014 |  |
|  |  |  | Updating of PowerPoint and Excel documents | Receipt of final clarifications from IGDRP members on PowerPoint and excel documents | 1 December 2014 |  |
|  |  |  |  | Collation and Circulation of final PowerPoint and excel documents | 31 January 2015 |  |
|  |  |  |  | Presentation of final draft to ASMF/DMF WG and Steering committee | Next IGDRP meeting |  |
| Deliverable - Common Quality Assessment Report (QAR)template and application form for ASMF/DMF |
| 4 | Development and adoption of a common QAR for ASMF/DMFs by IGDRP members | Review of existing QAR templates | Submission of existing ASMF/DMF templates by members | Uploading of ASMF/DMF templates by all IGDRP members | Completed | HC |
|  |  | Identification of desirable and mandatory features. | Using the Consortium QAR as a reference important difference to be highlighted for discussion. Consensus on desired features as an output. | Uploading of a Recommendation Document to IGDRP SP site outlining the agreed mandatory features of a common QAR template for ASMF/DMFs | Completed |  |
|  |  | Preparation of a common QAR template for ASMF/DMF | Template preparation | Circulation to members | Completed |  |
|  |  |  | Circulation of updated draft QAR template and list of issues to be discussed. | Circulation to members | Completed |  |
|  |  |  | Face to face discussion regarding template draft | Review of drafted QAR template Singapore Nov 2014 | Completed |  |
|  |  | Finalisation and acceptance of QAR template | Finalisation of QAR template | Circulation of updated draft to members | 1 December 2014 |  |
|  |  |  |  | Receipt of final clarifications from IGDRP members on QAR | 15 January 2015 |  |
|  |  |  |  | Collation and Circulation of final QAR template | 28 February 2015 |  |
|  |  |  | Acceptance of QAR template by ASMF/DMF members | Presentation of final draft to ASMF/DMF WG for final acceptance | Next IGDRP meeting |  |
|  |  | Implementation of QAR template by respective WG organisations | Preparation and updating of reference document recording implementation status. Note: Document to also capture barriers and issues related to implementation | Posting of reference document to SP site | To be updated as necessary |  |
| 5 | Development of Common administrative tools and requirements | Development of common features for an ASMF/DMF -application-form. | Submission of existing ASMF/DMF -application(submission)-forms by members | Uploading of ASMF/DMF -application-forms by all IGDRP members | Completed |  |
|  |  |  | Circulation of draft document and list of issues to be discussed. | Circulation to members | Completed | Co-Chair (WHO) |
|  |  |  | Discussion and consensus on desired features and their recommendations | Presentation and discussion with members | Completed |  |
|  |  |  | Revision of application form to reflect comments | Circulation of revised draft to members | 30 November2014 |  |
|  |  | Acceptance of the common ASMF/DMF -application-form features | Acceptance of common ASMF/DMF -application-form features. | Uploading to IGDRP SP of a document outlining the agreed common ASMF/DMF-application-form features. | 1 February 2015 |  |
|  |  | Implementation of the common application form features by respective WG members | Preparation and updating of reference document recording implementation status. Note: Document to also capture barriers and issues related to implementation | Posting of reference document to SP site | To be updated as necessary |  |
| Deliverable - Common assessor review guides |
| 6 | Assessor review guidance | Development of Assessor guidance for the assessment of ASMF/DMFs | Circulation of model Assessor Guidance to confirm format and style of Assessor guidance | Agreement on format/style of Assessor guidance | Completed | HSA |
|  |  |  | Drafting of model Assessor Guidance | Circulation to IGDRP members of the ACSS Assessor guidance as a basis for development of an IGDRP Assessors Guide | May 2015 |  |
|  |  |  |  | Collation of comments on Draft IGDRP Assessors Guide | November 2015 |  |
|  |  |  | Preparation of final draft of IGDRP Assessors Guide | Circulation to IGDRP members of s draft IGDRP Assessors Guide | Feb 2016 |  |
|  |  | Acceptance and implementation of an IGDRP Assessors Guide | Final acceptance of IGDRP Assessors Guide by members | Presentation of IGDRP ASMF/DMF Assessment Guidance to ASMF/DMF working group | May 2016 |  |
|  |  |  | Preparation and updating of reference document recording implementation status. Note: Document to also capture barriers and issues related to implementation | Posting of reference document to SP site | To be updated as necessary |  |
| Deliverable - Lexicon (glossary) |
| 7 | Development of a common lexicon among IGDRP members with respect to ASMF/DMFs (link to gap analysis) | Development of a common lexicon for the understanding of regional terminology | Creation of a pilot list of terminology as a basis for addition by IGDRP members | Circulation and posting of a pilot list of terminology on the IGDPR SP site. | Completed | HC |
|  |  |  | Circulation of second draft for comment | Circulation of next draft | 30 November 2014 |  |
|  |  |  |  | Receipt of comments from ASMF/DMF WG members | 15 January 2015 |  |
|  |  |  | Circulation of final version and agreement on lexicon | Circulation of final version and agreement on lexicon | 28 February 2015 |  |
| Deliverable – Guidance on instances when the submission of a separate ASMF/DMF should be made |
| 8 | Development of guidance describing the instances or criteria for which a separate ASMF/DMF should be filed. | Development of guidance describing the instances when a separate ASMF/DMF should be filed. | Circulation of questionnaire and “CMD EU document” to members | Circulation of questionnaire and “CMD EU document” to members | 30 November 2014 | Paul Marshall (EU) |
|  |  |  |  | Questionnaire returned and comments submitted by members | 31 January 2015 |  |
|  |  |  | Collation of comments and analysis of difference | Presentation of summary document outlining analysis | May 2015 |  |
|  |  |  | Preparation of draft guidance document | Circulation of draft guidance document to members | May 2015 |  |
|  |  |  |  | Comments on draft guidance received from IGDRP members | June 2015 |  |
|  |  | Acceptance and implementation of guidance describing the situations or criteria for which a separate ASMF/DMF should be filed. | Preparation of final draft | Acceptance of Guidance document of IGDRP members | November 2015 |  |
|  |  |  | Preparation and updating of reference document recording implementation status. Note: Document to also capture barriers and issues related to implementation | Posting of reference document to SP site | To be updated as necessary |  |
| Part II - Medium Term Goals: |
| Deliverable – Common technical requirements |
| 9 | Collaboration on issues related to the selection and justification of starting materials for the manufacture of drug substances | Discussion and sharing of information on the selection and justification of starting materials | Workplan and activities to be determined by 1 February 2014 | To be determined by 1 February 2014 | To be determined by 1 February 2014 | HC |
| Deliverable - A system for identifying common ASMFs/DMFs and their review status |
| 10 | Agreement over how this information should be made available to IGDRP members, including how and where this information will be stored, accessed, and maintained | Discussion and agreement over the manner in which this information will be shared (e.g., Centralised/decentralised? By enquiry/active publishing?) | Review of information requirements; members technical and legal ability to publish such information | Uploading of a recommendation document | To be determined | Identification of lead to be determined |
| 11 | Trial ASMF system for identifying common ASMFs/DMFs and their review status, (further discussions are required for next IGDRP meeting.) | Agreement over scope of a trial Agreement over location/manner of trial database. Database development Database population Database implementation Monitoring Review and recommendations Implementation |  |  | To be determined | Identification of lead to be determined |
| 12 | Determination of IGDRP members’ information sharing rights and abilities | Determination and review of IGDRP members’ rights and abilities for sharing confidential business information (CBI) contained in ASMF/DMFs |  |  | To be determined | ICMRA dependent |
| Part III – Long Term Goals: |
| Deliverable - Common administrative tools and requirements |
| 13 | Development of common coding systems for ASMF/DMFs and post-acceptance changes (variations) |  | Discussion and consensus on desired features of a common coding system for ASMF/DMF s and post-acceptance changes (variations) | Uploading of a Recommendation Document to IGDRP SP site outlining the agreed common coding system for ASMF/DMF s and post-acceptance changes (variations) | Next IGDRP meeting | identification of lead to be determined |
|  |  |  | Implementation of a common coding system for ASMF/DMF s and post-acceptance changes (variations) by IGDRP members | A summary document to be completed by IGDRP members identifying which members have adopted the common coding system and/or identifying any differences | Next IGDRP meeting | identification of lead to be determined |
| Deliverable - A system for accessing or exchanging assessment reports through a secure network and for addressing confidentiality issues |
| 14 | Agreement over how this information will be made available Agreement over where this information will be held |  |  |  | Next IGDRP meeting | identification of lead to be determined |
| Deliverable - Ability to share and utilise ASMF assessments from other regulatory agencies |
| 15 | Sharing and utilising ASMF assessments from other regulatory agencies |  |  |  | Next IGDRP meeting | identification of lead to be determined |
| Deliverable - A confidence building framework for establishing the equivalence of assessment systems |
| 16 | Confidence building framework for establishing the equivalence of assessment systems |  |  |  | Next IGDRP meeting | identification of lead to be determined |