ASMF/DMF Working Group
Work Plan
Updated: 8 October , 2014 (draft)

Part I - Short Term Goals:

Project #	Detailed Deliverable	Activity	Tasks	Milestone	Required completion Date	Lead person
Deliverable - Establishment of the Working Group (WG)
1	Acceptance of working group mandate document.	Drafting and agreement of an ASMF/DMF WG Mandate document	Drafting of ASMF/DMF WG Mandate document.	-	Completed	Co-Chair (TGA)
			Endorsement by ASMF/DMF WG members	-	Completed
			Finalisation of ASMF/DMF WG Mandate document	Mandate accepted with revision to PMDA reference, to be confirmed Tuesday	Completed
			Presentation and endorsement of the ASMF/DMF WG Mandate document to the IGDRP Steering Committee	Uploading of a finalised ASMF/DMF WG Mandate document to the Share Point site (SP)	Completed
2	Acceptance of ASMF/DMF working group members list	Drafting, circulation, and finalisation of ASMF/DMF WG membership list	Circulation of ASMF/DMF WG membership list (and contact information) for comments	-	Completed	Co-Chair (TGA)
			Finalisation of ASMF/DMF WG membership list	Uploading of a finalised ASMF/DMF Working Group Membership list to the SP site.	Completed
Deliverable – WG Survey
3	Survey of ASMF/DMF requirements and systems among IGDRP members	Circulation of a single survey covering information required from all deliverables	Circulation of draft Gap Analysis Survey		Completed	PMDA
			Receipt of comments on draft Gap Analysis Survey		Completed
			Circulation of finalised Gap Analysis Survey		Completed
			Collation of comments for a summary document outlining Gap Analysis Survey	Circulation of a summary document outlining Gap Analysis Survey	Completed
			Discussion on results of Gap Analysis Survey	Presentation a summary document outlining Gap Analysis Survey.	Completed
		Collation and presentation of results	Final draft of Gap Analysis Survey presented for comment	Presentation of final draft of the Gap Analysis Survey to ASMF/DMF WG and Steering committee	4 November 2014
			Updating of PowerPoint and Excel documents	Receipt of final clarifications from IGDRP members on PowerPoint and excel documents	1 December 2014
				Collation and Circulation of final PowerPoint and excel documents	31 January 2015
				Presentation of final draft to ASMF/DMF WG and Steering committee	Next IGDRP meeting
Deliverable - Common Quality Assessment Report (QAR)template and application form for ASMF/DMF
4	Development and adoption of a common QAR for ASMF/DMFs by IGDRP members	Review of existing QAR templates	Submission of existing ASMF/DMF templates by members	Uploading of ASMF/DMF templates by all IGDRP members	Completed	HC
		Identification of desirable and mandatory features.	Using the Consortium QAR as a reference important difference to be highlighted for discussion. Consensus on desired features as an output.	Uploading of a Recommendation Document to IGDRP SP site outlining the agreed mandatory features of a common QAR template for ASMF/DMFs	Completed
		Preparation of a common QAR template for ASMF/DMF	Template preparation	Circulation to members	Completed
			Circulation of updated draft QAR template and list of issues to be discussed.	Circulation to members	Completed
			Face to face discussion regarding template draft	Review of drafted QAR template / Singapore Nov 2014	Completed
		Finalisation and acceptance of QAR template	Finalisation of QAR template	Circulation of updated draft to members	1 December 2014
				Receipt of final clarifications from IGDRP members on QAR	15 January 2015
				Collation and Circulation of final QAR template	28 February 2015
			Acceptance of QAR template by ASMF/DMF members	Presentation of final draft to ASMF/DMF WG for final acceptance	Next IGDRP meeting
		Implementation of QAR template by respective WG organisations	Preparation and updating of reference document recording implementation status. / Note: Document to also capture barriers and issues related to implementation	Posting of reference document to SP site	To be updated as necessary
5	Development of Common administrative tools and requirements	Development of common features for an ASMF/DMF -application-form.	Submission of existing ASMF/DMF -application(submission)-forms by members	Uploading of ASMF/DMF -application-forms by all IGDRP members	Completed
			Circulation of draft document and list of issues to be discussed.	Circulation to members	Completed	Co-Chair (WHO)
			Discussion and consensus on desired features and their recommendations	Presentation and discussion with members	Completed
			Revision of application form to reflect comments	Circulation of revised draft to members	30 November2014
		Acceptance of the common ASMF/DMF -application-form features	Acceptance of common ASMF/DMF -application-form features.	Uploading to IGDRP SP of a document outlining the agreed common ASMF/DMF-application-form features.	1 February 2015
		Implementation of the common application form features by respective WG members	Preparation and updating of reference document recording implementation status. / Note: Document to also capture barriers and issues related to implementation	Posting of reference document to SP site	To be updated as necessary
Deliverable - Common assessor review guides
6	Assessor review guidance	Development of Assessor guidance for the assessment of ASMF/DMFs	Circulation of model Assessor Guidance to confirm format and style of Assessor guidance	Agreement on format/style of Assessor guidance	Completed	HSA
			Drafting of model Assessor Guidance	Circulation to IGDRP members of the ACSS Assessor guidance as a basis for development of an IGDRP Assessors Guide	May 2015
				Collation of comments on Draft IGDRP Assessors Guide	November 2015
			Preparation of final draft of IGDRP Assessors Guide	Circulation to IGDRP members of s draft IGDRP Assessors Guide	Feb 2016
		Acceptance and implementation of an IGDRP Assessors Guide	Final acceptance of IGDRP Assessors Guide by members	Presentation of IGDRP ASMF/DMF Assessment Guidance to ASMF/DMF working group	May 2016
			Preparation and updating of reference document recording implementation status. / Note: Document to also capture barriers and issues related to implementation	Posting of reference document to SP site	To be updated as necessary
Deliverable - Lexicon (glossary)
7	Development of a common lexicon among IGDRP members with respect to ASMF/DMFs (link to gap analysis)	Development of a common lexicon for the understanding of regional terminology	Creation of a pilot list of terminology as a basis for addition by IGDRP members	Circulation and posting of a pilot list of terminology on the IGDPR SP site.	Completed	HC
			Circulation of second draft for comment	Circulation of next draft	30 November 2014
				Receipt of comments from ASMF/DMF WG members	15 January 2015
			Circulation of final version / and agreement on lexicon	Circulation of final version / and agreement on lexicon	28 February 2015
Deliverable – Guidance on instances when the submission of a separate ASMF/DMF should be made
8	Development of guidance describing the instances or criteria for which a separate ASMF/DMF should be filed.	Development of guidance describing the instances when a separate ASMF/DMF should be filed.	Circulation of questionnaire and “CMD EU document” to members	Circulation of questionnaire and “CMD EU document” to members	30 November 2014	Paul Marshall (EU)
				Questionnaire returned and comments submitted by members	31 January 2015
			Collation of comments and analysis of difference	Presentation of summary document outlining analysis	May 2015
			Preparation of draft guidance document	Circulation of draft guidance document to members	May 2015
				Comments on draft guidance received from IGDRP members	June 2015
		Acceptance and implementation of guidance describing the situations or criteria for which a separate ASMF/DMF should be filed.	Preparation of final draft	Acceptance of Guidance document of IGDRP members	November 2015
			Preparation and updating of reference document recording implementation status. / Note: Document to also capture barriers and issues related to implementation	Posting of reference document to SP site	To be updated as necessary
Part II - Medium Term Goals:
Deliverable – Common technical requirements
9	Collaboration on issues related to the selection and justification of starting materials for the manufacture of drug substances	Discussion and sharing of information on the selection and justification of starting materials	Workplan and activities to be determined by 1 February 2014	To be determined by 1 February 2014	To be determined by 1 February 2014	HC
Deliverable - A system for identifying common ASMFs/DMFs and their review status
10	Agreement over how this information should be made available to IGDRP members, including how and where this information will be stored, accessed, and maintained	Discussion and agreement over the manner in which this information will be shared / (e.g., Centralised/decentralised? / By enquiry/active publishing?)	Review of information requirements; members technical and legal ability to publish such information	Uploading of a recommendation document	To be determined	Identification of lead to be determined
11	Trial ASMF system for identifying common ASMFs/DMFs and their review status, (further discussions are required for next IGDRP meeting.)	Agreement over scope of a trial / Agreement over location/manner of trial database. / Database development / Database population / Database implementation / Monitoring / Review and recommendations / Implementation			To be determined	Identification of lead to be determined
12	Determination of IGDRP members’ information sharing rights and abilities	Determination and review of IGDRP members’ rights and abilities for sharing confidential business information (CBI) contained in ASMF/DMFs			To be determined	ICMRA dependent
Part III – Long Term Goals:
Deliverable - Common administrative tools and requirements
13	Development of common coding systems for ASMF/DMFs and post-acceptance changes (variations)		Discussion and consensus on desired features of a common coding system for ASMF/DMF s and post-acceptance changes (variations)	Uploading of a Recommendation Document to IGDRP SP site outlining the agreed common coding system for ASMF/DMF s and post-acceptance changes (variations)	Next IGDRP meeting	identification of lead to be determined
			Implementation of a common coding system for ASMF/DMF s and post-acceptance changes (variations) by IGDRP members	A summary document to be completed by IGDRP members identifying which members have adopted the common coding system and/or identifying any differences	Next IGDRP meeting	identification of lead to be determined
Deliverable - A system for accessing or exchanging assessment reports through a secure network and for addressing confidentiality issues
14	Agreement over how this information will be made available / Agreement over where this information will be held				Next IGDRP meeting	identification of lead to be determined
Deliverable - Ability to share and utilise ASMF assessments from other regulatory agencies
15	Sharing and utilising ASMF assessments from other regulatory agencies				Next IGDRP meeting	identification of lead to be determined
Deliverable - A confidence building framework for establishing the equivalence of assessment systems
16	Confidence building framework for establishing the equivalence of assessment systems				Next IGDRP meeting	identification of lead to be determined